## Sheet1
Evergreen — Inventory Reporting Dashboard
ID | Task | Status | Owner | Target Start Date | Target End Date | Actual Start Date | Actual End Date | Comment
T01 | Project kick off meeting | In progress | Nina | Completed | 2026-09-21 | 2026-09-21
T02 | Requirement gathering | In progress | Leo | 2026-09-22 | 2026-12-02
T03 | Documentation | Pending | Sam | In progress | 2026-10-09
T04 | Development | Pending | Omar | 2026-10-12 | 2026-11-13
T05 | Unit Test | Pending | Omar | 2026-11-16 | 2026-11-20
T06 | Functional Test | Pending | Maya | 2026-11-23 | 2026-12-04
T07 | UAT | Pending | Leo | 2026-12-07 | 2026-12-11
T08 | Go-Live | Pending | Nina | 2026-12-15 | 2026-12-15