## Sheet1
Beacon — Employee Onboarding Portal
ID | Task | Status | Owner | Target Start Date | Target End Date | Actual Start Date | Actual End Date | Comment
T01 | Project kick off meeting | Completed | Priya | 2026-08-31 | 2026-08-31 | 2026-08-31
T02 | Requirement gathering | Pending | Nina | 2026-09-01 | 2026-11-25
T03 | Documentation | Pending | Maya | 2026-09-14 | 2026-12-04
T04 | Development | Pending | Sam | 2026-09-21 | 2026-10-23
T05 | Unit Test | Pending | Sam | 2026-10-26 | 2026-10-30
T06 | Functional Test | Pending | Omar | 2026-11-02 | 2026-11-13
T07 | UAT | Pending | Nina | 2026-11-16 | 2026-11-20
T08 | Go-Live | Pending | Priya | 2026-11-24 | 2026-11-24