## Sheet1
Cedar — Purchase Approval Workflow
ID | Task | Status | Owner | Target Start Date | Target End Date | Actual Start Date | Actual End Date | Comment
T01 | Project kick off meeting | Completed | Leo | 2026-09-08 | 2026-09-08 | 2026-09-08
T02 | Requirement gathering | Pending | Omar | 2026-09-09 | 2026-09-18
T03 | Documentation | Pending | Omar | 2026-09-21 | 2026-09-25
T04 | Development | Pending | Omar | 2026-09-28 | 2026-10-30
T05 | Unit Test | Pending | Omar | 2026-11-02 | 2026-11-07
T06 | Functional Test | Pending | Sam | 2026-11-09 | 2026-11-20
T07 | UAT | Pending | Priya | 2026-11-23 | 2026-12-02
T08 | Go-Live | Pending | Leo | 2026-12-04 | 2026-12-04