## Sheet1
Atlas — Equipment Loan Workflow
ID | Task | Status | Owner | Target Start Date | Target End Date | Actual Start Date | Actual End Date | Comment
T01 | Project kick off meeting | Completed | Maya | 2026-08-24 | 2026-08-24 | 2026-08-24
T02 | Requirement gathering | Pending | Leo | 2026-08-31 | 2026-09-07
T03 | Documentation | Pending | Nina | 2026-09-08 | 2026-09-15
T04 | Development | Pending | Omar | 2026-09-16 | 2026-10-16
T05 | Unit Test | Pending | Omar | 2026-10-19 | 2026-10-26
T06 | Functional Test | Pending | Priya | 2026-10-27 | 2026-11-06
T07 | UAT | Pending | Leo | 2026-11-09 | 2026-11-13
T08 | Go-Live | Pending | Maya | 2026-11-17 | 2026-11-17