## Sheet1
Delta — IT Service Request Portal
ID | Task | Status | Owner | Target Start Date | Target End Date | Actual Start Date | Actual End Date | Comment
T01 | Project kick off meeting | In progress | Omar | 2026-09-14 | 2026-09-14 | 2026-09-14
T02 | Requirement gathering | In progress | Maya | 2026-09-15 | 2026-11-23
T03 | Documentation | Pending | Leo | 2026-09-28 | 2026-10-02
T04 | Development | Pending | Sam | 2026-10-05 | 2026-11-06
T05 | Unit Test | Pending | Sam | 2026-11-09 | 2026-11-13
T06 | Functional Test | Pending | Nina | 2026-11-16 | 2026-11-25
T07 | UAT | Pending | Maya | 2026-11-30 | 2026-12-04
T08 | Go-Live | Pending | Omar | 2026-12-08 | 2026-12-08